## Status
MTRN4230 Asst 3 Requirements Tracking
Last updated | 20160520 |  | Group number |  |  | 5
Updated by | Vivek Desai
This Is the tasks that needed to first be completed before moving onto the above requirements
Date Due
RibStudio Operation |  | 2016-05-23 |  | Roshan/Linda |  | co-ordinates | multitasking | vacume/conveyor | niels
New GUI |  | 2016-05-23 |  | Xiangfen/Niels |  | Debug Tab | Sorting Tab | Order Management Tab
Image Detection |  | 2016-05-23 |  | Vivek/Niels |  | using surf point - refine | Image subtraction | box recognition | vivek
Code Flow Diagram |  | 2016-05-23 |  | Vivek/Linda
[7 empty] | Box image detection | Vivek
Requirement number | Marks | Status | Date last tested | Responsible person | Tested by | Title | Description | Comments
Picking up chocolates |  |  |  | (group member) | (group member)
1.1 | 1 | Pass. | 20160416 |  |  | Pick up easy chocolates | Picking up chocolates where none overlap and all are reachable.
1.2 | 1 | Pass. | 20160416 |  |  | Pick up overlap chocolates | Picking up all initially pickable chocolates where some overlap initially (up to 50% of visible area of a chocolate).
1.3 | 1 | Pass. | 20160416 |  |  | Pick up all chocolates | Picking up all reachable chocolates, including correctly removing pickable chocolates before those hidden underneath
1.4 | 1 | Pass. | 20160416 |  |  | Flipping all inverted chocolates | Flipping all reachable inverted chocolates so they face up
Stacking chocolates
2.1 | 1 | Pass. | 20160416 | y |  | Place one chocolate | Place a single chocolate in the given centre location and orientation
2.2 | 1 | Pass. | 20160416 | / |  | Place one chocolate of each flavour | Pick and place one of each kind of pickable chocolates in the following locations
2.2 | 1 | Pass. | 20160416 | / |  | Stack all chocolates | Neatly stack all visible chocolates into four piles with positions defined in the previous sub­section, accounting for the varying height of each pile
Load/Unload chocolates
3.1 | 1 | Fail. Solution known. | 20160416 |  |  | Load 1 chocolate into box | Load one chocolate into a box on the conveyor, regardless of position or orientation
3.2 | 1 | Fail. Solution known. | 20160416 |  |  | Load 4 chocolates into box | Load four chocolates into the four positions (B1 to B4) within a box on the conveyor so they all lie flat without overlap
3.3 | 1 | Fail. Solution known. | 20160416 |  |  | Unload 1 chocolate from box | Unload one chocolate onto the table from a box on the conveyor
3.4 | 1 | Fail. Solution unknown. | 20160416 |  |  | Unload all chocolates from box | Unload all chocolates onto the table from a box on the conveyor, where there will be at least 5 chocolates in the box, stacked neatly in the four positions (B1 to B4)
Basic order fulfilling
4.1 | 1 | Fail. Solution known. | 20160416 |  |  | Load one type of chocolate into box | To select one kind of the four kinds of chocolate and the number to be loaded into a single box
4.2 | 1 | Fail. Solution known. | 20160416 |  |  | Load multiple types of chocolates into box | To select multiple kinds of chocolates and the number of each to be loaded into a single box
4.3 | 1 | Fail. Solution known. | 20160416 |  |  | Load pattern of chocolates into box | To manually specify the pattern of chocolates to be loaded into a single box.
4.4 | 2 | Fail. Solution unknown. | 20160416 |  |  | Pause/stop and recover | To enable the motion of the robot to be stopped (order cancelled), paused (order maintained), restarted and to recover from e­stops
Advanced order fulfilling
5.1 | 1 | Fail. Solution unknown. | 20160416 |  |  | Possible to fulfil order? | Identify if it is possibly to fulfil the order and request a new order if it is not. You may need to unpack or flip chocolates before making this decision
5.2 | 5 | Fail. Solution known. | 20160416 |  |  | Fulfil order | Fulfil any order (as per the previous section) once the user has confirmed the pattern of chocolates. Display the current process status graphically at all times. Handle socket errors, e­stops and recover from unexpected events (such as dropped chocolates) smoothly with minimal user input.
Documentation and Project management
6.1 | 2 | Pass. | 20160416 | Vivek |  | Documentation | All of your functions must be well documented within the code in both Matlab and RAPID. Include at least a Help command, purpose / description, inputs, outputs, author, date last modified
6.2 | 2 | Pass. | 20160416 | Vivek |  | Requirements tracking | Make a requirements tracking spreadsheet of your own, and submit an electronic copy to your demonstrator in your lab time each week until week 13.
6.3 | 1 | Pass. | 20160416 | Vivek |  | Code management | The current status of your code management practices will be queried by your demonstrator each week. You need to provide evidence that you are securely and reliably managing versions of your code between group members, both for Matlab and RAPID. The easiest way to demonstrate this is through an online repository such as GitHub
6.4 | 3 | Fail. Solution known. | 20160416 | Vivek |  | Management report | You will need to provide a short report (<10 pages) detailing your project management practices and giving evidence of group members’ relative contributions based on requirements tracking and changelogs. This report should be uploaded with your code.
2016-05-23
Total | 30 | [8 empty] | 2016-05-23
are stacking locations clear | adam/xiafeng
stacking structures | Vivek
RobStudio | Linda/niel

## Working
Status
Fail. Solution unknown.
Fail. Solution known.
Pass.